## Roadmap
Order | Module | Name | Duration | Dependencies | Scheduling | Goal | Key Deliverables | Acceptance Summary | Module | Estimated weeks
0 | M00 | Platform Foundation | 2–3 weeks | None | Immediately | Create the shared platform capabilities that every later product module can use without sharing business logic or databases. | • Monorepo and service templates • Vue 3 platform shell and API gateway/BFF • Identity, workspace and site registration • Versioned event contracts • Dapr-based pub/sub abstraction • PostgreSQL, ClickHouse and object-storage development environment • OpenTelemetry-based logs, metrics and traces • Docker Compose self-hosted deployment • Azure Container Apps and Bicep baseline • CI validation and deployment workflows | • A user can sign in and register a website • Each service can be built and deployed independently • Services exchange versioned events without direct database access • The local stack can be started from documented commands • A minimal Azure development environment can be deployed from Bicep | M00 | 2.5
1 | M01 | Product Analytics | 4 weeks | M00 | After Platform Foundation | Measure real page views, sessions, visitors, acquisition sources, devices, countries and custom product events. | • Small JavaScript/TypeScript tracking SDK • High-throughput collection endpoint • Page-view, session and custom-event processing • Bot and duplicate filtering • ClickHouse analytics model and rollups • Overview, pages, sources, technology and geography dashboards • Live visitors view • Retention and privacy controls • Installation guide for anthony-air.nl | • The portfolio sends real analytics events • Events survive temporary processor failures • Dashboard metrics have documented definitions • A visitor can be excluded through privacy controls • Raw and processed event counts can be reconciled | M01 | 4
2 | M02 | Performance Monitoring | 3–4 weeks | M00; M01 optional | Any time after Foundation | Measure real-user performance and show where pages, devices or releases are slow. | • Web Vitals and navigation timing collection • Performance processing service • Percentile-based aggregations • Page, device and release comparison views • Performance budget configuration • Regression detection | • LCP, INP, CLS and TTFB can be queried by page and device • Slow samples are traceable without storing sensitive page content • Performance regressions can be compared against a prior period or release | M02 | 3.5
3 | M03 | Error Tracking | 3–4 weeks | M00 | Any time after Foundation | Capture browser and API errors, group similar failures and connect them to affected pages and releases. | • Browser error SDK integration • Unhandled exception and promise rejection capture • Error grouping and fingerprinting • Source-map upload workflow • Issue lifecycle and assignment • Error trends and affected-user dashboard | • Repeated occurrences group into one issue • Sensitive values are scrubbed before storage • A release can be associated with newly introduced errors | M03 | 3.5
4 | M04 | Deployment Intelligence | 2–3 weeks | M00 | Any time after Foundation | Record deployments and correlate product, performance and error changes with a release. | • GitHub Actions and generic webhook ingestion • Release and deployment data model • Deployment timeline • Version propagation through SDK events • Before/after comparison API • Release health summary | • Each production deployment appears in the platform • Analytics, performance and errors can be filtered by release • A release comparison uses explicit time windows and metric definitions | M04 | 2.5
5 | M05 | Goals and Funnels | 3 weeks | M01 | After Product Analytics | Measure conversions such as project views, CV downloads, contact actions and multi-step journeys. | • Goal definition interface • Event and page-based goals • Ordered funnel engine • Conversion and drop-off dashboards • Segmentation by source, device and campaign • Goal history and versioning | • A goal can be configured without redeploying the tracked website • Funnels clearly define ordering and attribution windows • Conversion values reconcile with underlying events | M05 | 3
6 | M06 | SEO and Content Quality | 3–4 weeks | M00 | Any time after Foundation | Inspect crawlability, metadata, links and technical SEO without coupling this work to analytics. | • Scheduled site crawler • Metadata and canonical checks • Broken-link detection • Sitemap and robots.txt validation • Lighthouse CLI worker • SEO issue dashboard and history | • A registered site can be crawled safely with limits • Findings include evidence and affected URLs • Historical scores can be compared between scans | M06 | 3.5
7 | M07 | Heatmaps and Session Insights | 4–6 weeks | M01 | After Product Analytics | Understand interaction patterns through privacy-aware click and scroll heatmaps, with session replay as an optional later slice. | • Normalized click-coordinate collection • Scroll-depth aggregation • Responsive viewport grouping • Click and scroll heatmap renderer • Aggressive input and text masking • Optional session replay proof of concept | • Heatmaps work across different viewport sizes • Form values and sensitive text are never collected • Storage and sampling limits can be configured per site | M07 | 5
8 | M08 | AI Insights | 3–5 weeks | At least one data module | After useful data exists | Use Claude to explain changes and suggest actions through controlled, typed analytics tools rather than unrestricted database access. | • AI provider abstraction • Typed metric-query tools • Weekly insight generation • Period and release comparison • Anomaly explanation workflow • Prompt versioning, audit and usage limits | • AI answers cite the metrics and periods used • Claude cannot query arbitrary tables or modify analytics data • Invalid tool arguments and unsupported conclusions are rejected | M08 | 4
9 | M09 | Alerts and Uptime | 3–4 weeks | M00; data modules optional | Any time after Foundation | Notify users about downtime, regressions, traffic anomalies and error spikes. | • Scheduled uptime checks • Rule-based alert engine • Email, Teams and webhook channels • Silencing and cooldown rules • Alert history and acknowledgement • Cross-module metric thresholds | • Alerts are deduplicated and rate limited • Failed notifications are retried • Rules can reference metrics without directly coupling services | M09 | 3.5
10 | M10 | Multi-site and Team Hardening | 3–4 weeks | M00 | When sharing the platform | Turn the personal platform into a safe multi-site product with teams, roles, quotas and lifecycle controls. | • Workspace roles and invitations • Per-site API keys and key rotation • Usage quotas and sampling controls • Data export and deletion workflows • Per-module access policies • Backup, restore and upgrade documentation | • One workspace cannot access another workspace's data • Keys can be rotated without service interruption • Data can be exported and deleted by site | M10 | 3.5
11 | M11 | C++ Edge Agent | 3–4 weeks | M00; M09 recommended | Optional specialist module | Learn C++ by creating a lightweight host agent that sends system health and availability observations. | • Cross-platform C++ agent • CPU, memory and disk metrics • HTTP and TCP health probes • Secure enrollment and configuration • Buffered offline delivery • Agent status dashboard | • The agent reconnects after network loss • Credentials are stored and transmitted securely • The module remains optional for normal website analytics | M11 | 3.5

## Asana Backlog
Name | Description | Section | Assignee | Collaborators | Due Date | Start Date | Parent Task | Dependencies | Module | Work Type | Priority | Estimate | Milestone | Status
M00 Milestone – Platform foundation ready | The shared platform can register sites, authenticate users, exchange events and run locally or on Azure. | M00 – Platform Foundation | [6 empty] | M00 | Milestone | High |  | M00 Complete | Backlog
Epic M00.1 – Product and architecture decisions | Define the platform boundaries before implementation. | M00 – Platform Foundation | [6 empty] | M00 | Epic | High | 3 days |  | Backlog
Write product vision and scope | Document target users, core problem, non-goals and the relationship between analytics, observability and AI. | M00 – Platform Foundation |  |  |  |  | Epic M00.1 – Product and architecture decisions |  | M00 | Task | High |  |  | Backlog
Create C4 context diagram | Show tracked websites, users, external identity, AI provider and hosting environments. | M00 – Platform Foundation |  |  |  |  | Epic M00.1 – Product and architecture decisions |  | M00 | Task | High |  |  | Backlog
Create C4 container diagram | Show dashboard, gateway, platform services, collectors, workers, brokers and databases. | M00 – Platform Foundation |  |  |  |  | Epic M00.1 – Product and architecture decisions |  | M00 | Task | High |  |  | Backlog
Define bounded contexts and data ownership | State which service owns each entity and forbid direct access to another service's tables. | M00 – Platform Foundation |  |  |  |  | Epic M00.1 – Product and architecture decisions |  | M00 | Task | High |  |  | Backlog
Create ADR: service-oriented modular platform | Explain why modules are independently deployable but may share one monorepo. | M00 – Platform Foundation |  |  |  |  | Epic M00.1 – Product and architecture decisions |  | M00 | Task | High |  |  | Backlog
Create ADR: Dapr pub/sub abstraction | Document broker portability between local self-hosting and Azure. | M00 – Platform Foundation |  |  |  |  | Epic M00.1 – Product and architecture decisions |  | M00 | Task | High |  |  | Backlog
Create ADR: PostgreSQL plus ClickHouse | Document metadata versus event-analytics storage responsibilities. | M00 – Platform Foundation |  |  |  |  | Epic M00.1 – Product and architecture decisions |  | M00 | Task | High |  |  | Backlog
Create privacy threat model | Identify identifiers, IP handling, referrers, URLs, query strings and sensitive DOM content risks. | M00 – Platform Foundation |  |  |  |  | Epic M00.1 – Product and architecture decisions |  | M00 | Task | High |  |  | Backlog
Epic M00.2 – Repository and service templates | Create repeatable project templates for services and workers. | M00 – Platform Foundation | [6 empty] | M00 | Epic | High | 3 days |  | Backlog
Create monorepo structure | Add apps, services, packages, infrastructure, tests and docs folders. | M00 – Platform Foundation |  |  |  |  | Epic M00.2 – Repository and service templates |  | M00 | Task | Medium |  |  | Backlog
Create ASP.NET Core API template | Include health checks, ProblemDetails, validation, logging and OpenTelemetry. | M00 – Platform Foundation |  |  |  |  | Epic M00.2 – Repository and service templates |  | M00 | Task | Medium |  |  | Backlog
Create .NET worker template | Include graceful shutdown, retries, idempotency hooks and tracing. | M00 – Platform Foundation |  |  |  |  | Epic M00.2 – Repository and service templates |  | M00 | Task | Medium |  |  | Backlog
Create Vue 3 dashboard shell | Configure TypeScript, Pinia, Router, i18n, API client and authentication boundaries. | M00 – Platform Foundation |  |  |  |  | Epic M00.2 – Repository and service templates |  | M00 | Task | Medium |  |  | Backlog
Create shared event-contract package | Store versioned JSON schemas or strongly typed contracts without sharing domain models. | M00 – Platform Foundation |  |  |  |  | Epic M00.2 – Repository and service templates |  | M00 | Task | Medium |  |  | Backlog
Add code formatting and linting | Use consistent .NET and TypeScript formatting in local and CI workflows. | M00 – Platform Foundation |  |  |  |  | Epic M00.2 – Repository and service templates |  | M00 | Task | Medium |  |  | Backlog
Create contribution and branching guide | Define issue, branch, commit, pull request and release conventions. | M00 – Platform Foundation |  |  |  |  | Epic M00.2 – Repository and service templates |  | M00 | Task | Medium |  |  | Backlog
Epic M00.3 – Local self-hosted runtime | Run the entire development platform without paid cloud dependencies. | M00 – Platform Foundation | [6 empty] | M00 | Epic | High | 4 days |  | Backlog
Create Docker Compose stack | Run gateway, services, PostgreSQL, ClickHouse, RabbitMQ, Redis and MinIO as required. | M00 – Platform Foundation |  |  |  |  | Epic M00.3 – Local self-hosted runtime |  | M00 | Task | High |  |  | Backlog
Configure Dapr self-hosted sidecars | Use local pub/sub and service invocation components. | M00 – Platform Foundation |  |  |  |  | Epic M00.3 – Local self-hosted runtime |  | M00 | Task | High |  |  | Backlog
Add database initialization scripts | Create service-owned databases, schemas and local users. | M00 – Platform Foundation |  |  |  |  | Epic M00.3 – Local self-hosted runtime |  | M00 | Task | High |  |  | Backlog
Add local secret management | Document development-only secrets and prevent committing them. | M00 – Platform Foundation |  |  |  |  | Epic M00.3 – Local self-hosted runtime |  | M00 | Task | High |  |  | Backlog
Add health overview command | Provide one command or script to verify all containers and dependencies. | M00 – Platform Foundation |  |  |  |  | Epic M00.3 – Local self-hosted runtime |  | M00 | Task | High |  |  | Backlog
Create seed data workflow | Create a demo workspace, site and representative events. | M00 – Platform Foundation |  |  |  |  | Epic M00.3 – Local self-hosted runtime |  | M00 | Task | High |  |  | Backlog
Document NAS deployment profile | Describe volumes, backups, reverse proxy, TLS and resource limits for the user's NAS. | M00 – Platform Foundation |  |  |  |  | Epic M00.3 – Local self-hosted runtime |  | M00 | Task | High |  |  | Backlog
Epic M00.4 – Identity, workspaces and sites | Provide the shared control plane for all modules. | M00 – Platform Foundation | [6 empty] | M00 | Epic | High | 1 week |  | Backlog
Integrate Microsoft Entra ID authentication | Authenticate dashboard users and validate API access tokens. | M00 – Platform Foundation |  |  |  |  | Epic M00.4 – Identity, workspaces and sites |  | M00 | Task | High |  |  | Backlog
Implement workspace entity | Create a tenant boundary even when only one personal workspace exists. | M00 – Platform Foundation |  |  |  |  | Epic M00.4 – Identity, workspaces and sites |  | M00 | Task | High |  |  | Backlog
Implement membership and roles | Add Owner, Admin, Developer and Viewer policies. | M00 – Platform Foundation |  |  |  |  | Epic M00.4 – Identity, workspaces and sites |  | M00 | Task | High |  |  | Backlog
Implement site registration | Store name, canonical domain, allowed origins, timezone and environment. | M00 – Platform Foundation |  |  |  |  | Epic M00.4 – Identity, workspaces and sites |  | M00 | Task | High |  |  | Backlog
Implement site SDK key issuance | Generate scoped publish keys that cannot read analytics. | M00 – Platform Foundation |  |  |  |  | Epic M00.4 – Identity, workspaces and sites |  | M00 | Task | High |  |  | Backlog
Implement key rotation | Allow overlapping keys during safe migration. | M00 – Platform Foundation |  |  |  |  | Epic M00.4 – Identity, workspaces and sites |  | M00 | Task | High |  |  | Backlog
Implement module enablement settings | Allow analytics, performance, errors and later modules to be toggled independently. | M00 – Platform Foundation |  |  |  |  | Epic M00.4 – Identity, workspaces and sites |  | M00 | Task | High |  |  | Backlog
Build workspace and site settings UI | Create the first usable dashboard settings screens. | M00 – Platform Foundation |  |  |  |  | Epic M00.4 – Identity, workspaces and sites |  | M00 | Task | High |  |  | Backlog
Epic M00.5 – Messaging, observability and CI/CD | Create reliable integration and delivery foundations. | M00 – Platform Foundation | [6 empty] | M00 | Epic | High | 1 week |  | Backlog
Define CloudEvent envelope conventions | Standardize event ID, type, version, time, source, tenant and correlation fields. | M00 – Platform Foundation |  |  |  |  | Epic M00.5 – Messaging, observability and CI/CD |  | M00 | Task | High |  |  | Backlog
Implement event publisher abstraction | Services publish through Dapr rather than a broker-specific SDK. | M00 – Platform Foundation |  |  |  |  | Epic M00.5 – Messaging, observability and CI/CD |  | M00 | Task | High |  |  | Backlog
Implement consumer idempotency pattern | Persist processed event IDs or use safe natural keys. | M00 – Platform Foundation |  |  |  |  | Epic M00.5 – Messaging, observability and CI/CD |  | M00 | Task | High |  |  | Backlog
Configure distributed tracing | Propagate correlation and trace identifiers through HTTP and pub/sub. | M00 – Platform Foundation |  |  |  |  | Epic M00.5 – Messaging, observability and CI/CD |  | M00 | Task | High |  |  | Backlog
Create pull-request CI workflow | Build, lint and test .NET and TypeScript projects. | M00 – Platform Foundation |  |  |  |  | Epic M00.5 – Messaging, observability and CI/CD |  | M00 | Task | High |  |  | Backlog
Create container build workflow | Produce versioned images for independently deployable services. | M00 – Platform Foundation |  |  |  |  | Epic M00.5 – Messaging, observability and CI/CD |  | M00 | Task | High |  |  | Backlog
Create Bicep baseline | Provision Container Apps environment, registry, observability and secret resources. | M00 – Platform Foundation |  |  |  |  | Epic M00.5 – Messaging, observability and CI/CD |  | M00 | Task | High |  |  | Backlog
Create Azure development deployment | Deploy the control plane and one sample service. | M00 – Platform Foundation |  |  |  |  | Epic M00.5 – Messaging, observability and CI/CD |  | M00 | Task | High |  |  | Backlog
Document rollback and database migration rules | Separate backward-compatible rollout from destructive migrations. | M00 – Platform Foundation |  |  |  |  | Epic M00.5 – Messaging, observability and CI/CD |  | M00 | Task | High |  |  | Backlog
M01 Milestone – Portfolio analytics live | anthony-air.nl sends real traffic to the self-hosted platform and the dashboard reports trusted page, visitor and acquisition metrics. | M01 – Product Analytics | [5 empty] | M00 Milestone – Platform foundation ready | M01 | Milestone | High |  | M01 Complete | Backlog
Epic M01.1 – Analytics definitions and privacy model | Define exactly what each metric means before collecting data. | M01 – Product Analytics | [6 empty] | M01 | Epic | High | 3 days |  | Backlog
Define page-view rules | Document SPA navigation, reloads, redirects, excluded routes and canonical URL handling. | M01 – Product Analytics |  |  |  |  | Epic M01.1 – Analytics definitions and privacy model |  | M01 | Task | High |  |  | Backlog
Define session rules | Choose inactivity timeout, cross-tab behavior and when a session restarts. | M01 – Product Analytics |  |  |  |  | Epic M01.1 – Analytics definitions and privacy model |  | M01 | Task | High |  |  | Backlog
Define visitor rules | Use privacy-preserving daily or configurable identifiers and explain limitations. | M01 – Product Analytics |  |  |  |  | Epic M01.1 – Analytics definitions and privacy model |  | M01 | Task | High |  |  | Backlog
Define bounce and engagement rules | Avoid copying ambiguous Google Analytics terms without a clear formula. | M01 – Product Analytics |  |  |  |  | Epic M01.1 – Analytics definitions and privacy model |  | M01 | Task | High |  |  | Backlog
Define active-time measurement | Pause timers when the page is hidden or the user is inactive. | M01 – Product Analytics |  |  |  |  | Epic M01.1 – Analytics definitions and privacy model |  | M01 | Task | High |  |  | Backlog
Define URL and query-string policy | Allowlist campaign parameters and strip tokens or personal information. | M01 – Product Analytics |  |  |  |  | Epic M01.1 – Analytics definitions and privacy model |  | M01 | Task | High |  |  | Backlog
Define IP and geography policy | Use IP only transiently for coarse enrichment and avoid persistent raw IP storage. | M01 – Product Analytics |  |  |  |  | Epic M01.1 – Analytics definitions and privacy model |  | M01 | Task | High |  |  | Backlog
Define retention and deletion rules | Specify raw-event, aggregate and audit retention per site. | M01 – Product Analytics |  |  |  |  | Epic M01.1 – Analytics definitions and privacy model |  | M01 | Task | High |  |  | Backlog
Epic M01.2 – Browser tracking SDK | Create a small, reliable and privacy-aware TypeScript SDK. | M01 – Product Analytics | [6 empty] | M01 | Epic | High | 1 week |  | Backlog
Create SDK package and build pipeline | Publish browser, ESM and optional npm outputs with versioning. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Implement initialization and configuration | Accept site key, endpoint, environment, consent state and sampling options. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Implement SPA page-view tracking | Track Vue Router navigation without double-counting initial loads. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Implement referrer and campaign parsing | Normalize direct, search, social, referral and UTM acquisition data. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Implement session identifier | Use session-scoped storage and reset based on documented rules. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Implement privacy-preserving visitor identifier | Avoid fingerprinting and make persistence an explicit configuration decision. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Implement engagement and active-time tracking | Send bounded heartbeats or a final summary using resilient browser APIs. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Implement custom event API | Expose track(name, properties) with schema limits and blocked property names. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Implement batching and retry | Batch events, cap memory and tolerate temporary network failure. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Implement consent and opt-out API | Do not send events until the configured privacy condition is satisfied. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Implement SDK debug mode | Show payloads and validation errors without sending production data. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Add SDK unit and browser tests | Test navigation, visibility changes, batching, opt-out and malformed input. | M01 – Product Analytics |  |  |  |  | Epic M01.2 – Browser tracking SDK |  | M01 | Task | High |  |  | Backlog
Epic M01.3 – Collection API | Accept events rapidly without performing analytics queries or heavy processing. | M01 – Product Analytics | [6 empty] | M01 | Epic | High | 4 days |  | Backlog
Create POST /v1/events endpoint | Accept batched, versioned browser events. | M01 – Product Analytics |  |  |  |  | Epic M01.3 – Collection API |  | M01 | Task | High |  |  | Backlog
Validate site key and allowed origin | Reject unknown sites, disabled modules and unauthorized origins. | M01 – Product Analytics |  |  |  |  | Epic M01.3 – Collection API |  | M01 | Task | High |  |  | Backlog
Validate event schemas | Return useful development errors while keeping production responses minimal. | M01 – Product Analytics |  |  |  |  | Epic M01.3 – Collection API |  | M01 | Task | High |  |  | Backlog
Apply payload and rate limits | Protect the collector from oversized or abusive requests. | M01 – Product Analytics |  |  |  |  | Epic M01.3 – Collection API |  | M01 | Task | High |  |  | Backlog
Generate trusted server metadata | Assign receive time, request ID and coarse network metadata server-side. | M01 – Product Analytics |  |  |  |  | Epic M01.3 – Collection API |  | M01 | Task | High |  |  | Backlog
Publish accepted events | Send validated CloudEvents through the pub/sub abstraction. | M01 – Product Analytics |  |  |  |  | Epic M01.3 – Collection API |  | M01 | Task | High |  |  | Backlog
Implement duplicate request protection | Use event IDs to safely handle client retries. | M01 – Product Analytics |  |  |  |  | Epic M01.3 – Collection API |  | M01 | Task | High |  |  | Backlog
Add collector load test | Measure throughput and latency using realistic event batches. | M01 – Product Analytics |  |  |  |  | Epic M01.3 – Collection API |  | M01 | Task | High |  |  | Backlog
Epic M01.4 – Analytics processing pipeline | Turn accepted browser events into trusted analytics records. | M01 – Product Analytics | [6 empty] | M01 | Epic | High | 1 week |  | Backlog
Create analytics event consumer | Consume page views, engagement events and custom events independently. | M01 – Product Analytics |  |  |  |  | Epic M01.4 – Analytics processing pipeline |  | M01 | Task | High |  |  | Backlog
Normalize URLs and page titles | Apply site rules before persistence. | M01 – Product Analytics |  |  |  |  | Epic M01.4 – Analytics processing pipeline |  | M01 | Task | High |  |  | Backlog
Normalize referrer and campaign data | Create stable channel, source, medium and campaign fields. | M01 – Product Analytics |  |  |  |  | Epic M01.4 – Analytics processing pipeline |  | M01 | Task | High |  |  | Backlog
Enrich device and browser categories | Use bounded categories rather than storing full high-entropy fingerprints. | M01 – Product Analytics |  |  |  |  | Epic M01.4 – Analytics processing pipeline |  | M01 | Task | High |  |  | Backlog
Enrich coarse geography | Map transient network data to allowed country or region fields. | M01 – Product Analytics |  |  |  |  | Epic M01.4 – Analytics processing pipeline |  | M01 | Task | High |  |  | Backlog
Implement bot filtering | Mark rather than silently delete suspicious events so quality can be inspected. | M01 – Product Analytics |  |  |  |  | Epic M01.4 – Analytics processing pipeline |  | M01 | Task | High |  |  | Backlog
Implement event deduplication | Prevent retry duplicates from affecting metrics. | M01 – Product Analytics |  |  |  |  | Epic M01.4 – Analytics processing pipeline |  | M01 | Task | High |  |  | Backlog
Persist normalized events to ClickHouse | Use partitioning and ordering suited to site and time queries. | M01 – Product Analytics |  |  |  |  | Epic M01.4 – Analytics processing pipeline |  | M01 | Task | High |  |  | Backlog
Publish analytics.processed event | Allow funnels, alerts and AI to subscribe later. | M01 – Product Analytics |  |  |  |  | Epic M01.4 – Analytics processing pipeline |  | M01 | Task | High |  |  | Backlog
Create dead-letter recovery command | Inspect, fix and replay failed messages safely. | M01 – Product Analytics |  |  |  |  | Epic M01.4 – Analytics processing pipeline |  | M01 | Task | High |  |  | Backlog
Epic M01.5 – Analytics storage and aggregation | Create a queryable analytics model with transparent calculations. | M01 – Product Analytics | [6 empty] | M01 | Epic | High | 1 week |  | Backlog
Design raw analytics event table | Store normalized immutable events with site and event version. | M01 – Product Analytics |  |  |  |  | Epic M01.5 – Analytics storage and aggregation |  | M01 | Task | High |  |  | Backlog
Design session aggregation | Calculate session start, end, duration, landing and exit pages. | M01 – Product Analytics |  |  |  |  | Epic M01.5 – Analytics storage and aggregation |  | M01 | Task | High |  |  | Backlog
Design daily site rollup | Pre-aggregate common overview metrics by site and date. | M01 – Product Analytics |  |  |  |  | Epic M01.5 – Analytics storage and aggregation |  | M01 | Task | High |  |  | Backlog
Design page rollup | Aggregate views, visitors, engagement and exits by page. | M01 – Product Analytics |  |  |  |  | Epic M01.5 – Analytics storage and aggregation |  | M01 | Task | High |  |  | Backlog
Design acquisition rollup | Aggregate channels, referrers and campaigns. | M01 – Product Analytics |  |  |  |  | Epic M01.5 – Analytics storage and aggregation |  | M01 | Task | High |  |  | Backlog
Design technology rollup | Aggregate device, browser, OS and viewport categories. | M01 – Product Analytics |  |  |  |  | Epic M01.5 – Analytics storage and aggregation |  | M01 | Task | High |  |  | Backlog
Design geography rollup | Aggregate only the configured geographic granularity. | M01 – Product Analytics |  |  |  |  | Epic M01.5 – Analytics storage and aggregation |  | M01 | Task | High |  |  | Backlog
Implement late-event handling | Recalculate affected windows when delayed events arrive. | M01 – Product Analytics |  |  |  |  | Epic M01.5 – Analytics storage and aggregation |  | M01 | Task | High |  |  | Backlog
Implement data reconciliation job | Compare accepted, processed, filtered and stored event counts. | M01 – Product Analytics |  |  |  |  | Epic M01.5 – Analytics storage and aggregation |  | M01 | Task | High |  |  | Backlog
Add retention and partition cleanup | Delete expired data without blocking normal queries. | M01 – Product Analytics |  |  |  |  | Epic M01.5 – Analytics storage and aggregation |  | M01 | Task | High |  |  | Backlog
Epic M01.6 – Analytics query API | Expose stable metric APIs rather than allowing the dashboard to query ClickHouse directly. | M01 – Product Analytics | [6 empty] | M01 | Epic | High | 4 days |  | Backlog
Create overview metrics endpoint | Return visitors, sessions, views, engagement, bounce and duration with definitions. | M01 – Product Analytics |  |  |  |  | Epic M01.6 – Analytics query API |  | M01 | Task | High |  |  | Backlog
Create time-series endpoint | Support hour, day, week and month intervals. | M01 – Product Analytics |  |  |  |  | Epic M01.6 – Analytics query API |  | M01 | Task | High |  |  | Backlog
Create page metrics endpoint | Support search, sorting, pagination and route filters. | M01 – Product Analytics |  |  |  |  | Epic M01.6 – Analytics query API |  | M01 | Task | High |  |  | Backlog
Create acquisition endpoint | Return channels, sources, referrers and campaigns. | M01 – Product Analytics |  |  |  |  | Epic M01.6 – Analytics query API |  | M01 | Task | High |  |  | Backlog
Create technology endpoint | Return device, browser, OS and screen categories. | M01 – Product Analytics |  |  |  |  | Epic M01.6 – Analytics query API |  | M01 | Task | High |  |  | Backlog
Create geography endpoint | Return country or configured regional aggregates. | M01 – Product Analytics |  |  |  |  | Epic M01.6 – Analytics query API |  | M01 | Task | High |  |  | Backlog
Create custom-event endpoint | Return event counts, unique sessions and allowed properties. | M01 – Product Analytics |  |  |  |  | Epic M01.6 – Analytics query API |  | M01 | Task | High |  |  | Backlog
Implement comparison periods | Return current and previous values using explicit periods. | M01 – Product Analytics |  |  |  |  | Epic M01.6 – Analytics query API |  | M01 | Task | High |  |  | Backlog
Add site and workspace authorization | Enforce ownership in every query. | M01 – Product Analytics |  |  |  |  | Epic M01.6 – Analytics query API |  | M01 | Task | High |  |  | Backlog
Add query cache and timeout limits | Protect ClickHouse from repeated expensive dashboard requests. | M01 – Product Analytics |  |  |  |  | Epic M01.6 – Analytics query API |  | M01 | Task | High |  |  | Backlog
Epic M01.7 – Analytics dashboard | Build a useful Vue dashboard for real portfolio traffic. | M01 – Product Analytics | [6 empty] | M01 | Epic | High | 1 week |  | Backlog
Create site and date-range selector | Persist dashboard state in the route so views are shareable. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Create overview metric cards | Show values, comparison and metric definitions. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Create traffic time-series view | Support views, visitors and sessions without misleading scales. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Create top pages table | Show views, visitors, engagement and exit metrics. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Create acquisition views | Show channels, referrers and campaigns. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Create technology views | Show device, browser and OS breakdowns. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Create geography view | Show a table first; add a map only when it improves interpretation. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Create custom-event explorer | Filter named events and inspect allowed property breakdowns. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Create filters and segments | Support page, source, device and country filters. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Create metric glossary drawer | Explain visitor, session, bounce, duration and comparison calculations. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Add responsive and accessible states | Support keyboard use, readable tables, loading, errors and empty data. | M01 – Product Analytics |  |  |  |  | Epic M01.7 – Analytics dashboard |  | M01 | Task | High |  |  | Backlog
Epic M01.8 – Live analytics, quality and launch | Finish the module with trustworthy operation and a real deployment. | M01 – Product Analytics | [6 empty] | M01 | Epic | High | 4 days |  | Backlog
Implement live visitor projection | Maintain a short-lived count and current-page list without treating it as durable truth. | M01 – Product Analytics |  |  |  |  | Epic M01.8 – Live analytics, quality and launch |  | M01 | Task | High |  |  | Backlog
Add SignalR live updates | Update the live panel without polling the main query APIs. | M01 – Product Analytics |  |  |  |  | Epic M01.8 – Live analytics, quality and launch |  | M01 | Task | High |  |  | Backlog
Create data-quality dashboard | Show accepted, rejected, duplicate, bot, delayed and failed events. | M01 – Product Analytics |  |  |  |  | Epic M01.8 – Live analytics, quality and launch |  | M01 | Task | High |  |  | Backlog
Create site installation snippet | Generate a copyable SDK integration for anthony-air.nl. | M01 – Product Analytics |  |  |  |  | Epic M01.8 – Live analytics, quality and launch |  | M01 | Task | High |  |  | Backlog
Install SDK on portfolio staging | Verify routes, referrers, events and privacy behavior. | M01 – Product Analytics |  |  |  |  | Epic M01.8 – Live analytics, quality and launch |  | M01 | Task | High |  |  | Backlog
Run synthetic acceptance traffic | Use known test journeys and reconcile expected metrics. | M01 – Product Analytics |  |  |  |  | Epic M01.8 – Live analytics, quality and launch |  | M01 | Task | High |  |  | Backlog
Deploy analytics module to self-hosted environment | Use the NAS profile and production TLS. | M01 – Product Analytics |  |  |  |  | Epic M01.8 – Live analytics, quality and launch |  | M01 | Task | High |  |  | Backlog
Create backup and restore test | Verify metadata and analytics data recovery procedures. | M01 – Product Analytics |  |  |  |  | Epic M01.8 – Live analytics, quality and launch |  | M01 | Task | High |  |  | Backlog
Write module runbook | Document health checks, replay, retention and common failures. | M01 – Product Analytics |  |  |  |  | Epic M01.8 – Live analytics, quality and launch |  | M01 | Task | High |  |  | Backlog
Publish portfolio case study | Explain architecture, trade-offs, privacy, screenshots and real findings. | M01 – Product Analytics |  |  |  |  | Epic M01.8 – Live analytics, quality and launch |  | M01 | Task | High |  |  | Backlog
M02 Milestone – Performance Monitoring ready | The performance monitoring module is independently deployable, observable and available in the shared dashboard. | M02 – Performance Monitoring | [6 empty] | M02 | Milestone | High |  | M02 Complete | Backlog
Epic M02.1 – Performance event collection | Collect real-user measurements without slowing the website. | M02 – Performance Monitoring | [6 empty] | M02 | Epic | High | 1 week |  | Backlog
Extend SDK with Web Vitals | Collect LCP, INP and CLS with page and navigation context. | M02 – Performance Monitoring |  |  |  |  | Epic M02.1 – Performance event collection |  | M02 | Task | Medium |  |  | Backlog
Collect navigation timing | Capture TTFB, DNS, connection and DOM timing fields that are stable and useful. | M02 – Performance Monitoring |  |  |  |  | Epic M02.1 – Performance event collection |  | M02 | Task | Medium |  |  | Backlog
Add configurable sampling | Limit volume per site, page and device class. | M02 – Performance Monitoring |  |  |  |  | Epic M02.1 – Performance event collection |  | M02 | Task | Medium |  |  | Backlog
Publish performance events | Route performance payloads through the existing collector and versioned contracts. | M02 – Performance Monitoring |  |  |  |  | Epic M02.1 – Performance event collection |  | M02 | Task | Medium |  |  | Backlog
Test SDK overhead | Measure bundle size, execution time and network impact. | M02 – Performance Monitoring |  |  |  |  | Epic M02.1 – Performance event collection |  | M02 | Task | Medium |  |  | Backlog
Epic M02.2 – Processing and storage | Create independent performance data ownership. | M02 – Performance Monitoring | [6 empty] | M02 | Epic | High | 1 week |  | Backlog
Create Performance Service | Own processing, storage, queries and budgets for performance data. | M02 – Performance Monitoring |  |  |  |  | Epic M02.2 – Processing and storage |  | M02 | Task | Medium |  |  | Backlog
Create performance ClickHouse schema | Optimize percentiles by site, page, device, release and time. | M02 – Performance Monitoring |  |  |  |  | Epic M02.2 – Processing and storage |  | M02 | Task | Medium |  |  | Backlog
Implement outlier and invalid-sample filtering | Preserve quality flags for diagnostics. | M02 – Performance Monitoring |  |  |  |  | Epic M02.2 – Processing and storage |  | M02 | Task | Medium |  |  | Backlog
Implement percentile rollups | Calculate p50, p75, p90 and p95 rather than relying only on averages. | M02 – Performance Monitoring |  |  |  |  | Epic M02.2 – Processing and storage |  | M02 | Task | Medium |  |  | Backlog
Subscribe to deployment events | Attach known release versions without direct database access. | M02 – Performance Monitoring |  |  |  |  | Epic M02.2 – Processing and storage |  | M02 | Task | Medium |  |  | Backlog
Epic M02.3 – Performance dashboard and regressions | Turn measurements into decisions. | M02 – Performance Monitoring | [6 empty] | M02 | Epic | High | 1 week |  | Backlog
Create Core Web Vitals overview | Show distributions and pass/needs-improvement/poor categories. | M02 – Performance Monitoring |  |  |  |  | Epic M02.3 – Performance dashboard and regressions |  | M02 | Task | Medium |  |  | Backlog
Create page performance table | Compare pages and sample counts. | M02 – Performance Monitoring |  |  |  |  | Epic M02.3 – Performance dashboard and regressions |  | M02 | Task | Medium |  |  | Backlog
Create device and browser segments | Identify mobile or browser-specific slowdowns. | M02 – Performance Monitoring |  |  |  |  | Epic M02.3 – Performance dashboard and regressions |  | M02 | Task | Medium |  |  | Backlog
Create release comparison | Compare before and after deployment windows. | M02 – Performance Monitoring |  |  |  |  | Epic M02.3 – Performance dashboard and regressions |  | M02 | Task | Medium |  |  | Backlog
Implement performance budgets | Allow per-site and per-page thresholds. | M02 – Performance Monitoring |  |  |  |  | Epic M02.3 – Performance dashboard and regressions |  | M02 | Task | Medium |  |  | Backlog
Create regression event | Publish a typed event when a sustained budget regression occurs. | M02 – Performance Monitoring |  |  |  |  | Epic M02.3 – Performance dashboard and regressions |  | M02 | Task | Medium |  |  | Backlog
M03 Milestone – Error Tracking ready | The error tracking module is independently deployable, observable and available in the shared dashboard. | M03 – Error Tracking | [6 empty] | M03 | Milestone | High |  | M03 Complete | Backlog
Epic M03.1 – Error capture | Capture failures safely from browser and backend applications. | M03 – Error Tracking | [6 empty] | M03 | Epic | High | 1 week |  | Backlog
Add window error capture | Collect uncaught browser errors with bounded context. | M03 – Error Tracking |  |  |  |  | Epic M03.1 – Error capture |  | M03 | Task | Medium |  |  | Backlog
Add unhandled rejection capture | Capture rejected promises and normalized reasons. | M03 – Error Tracking |  |  |  |  | Epic M03.1 – Error capture |  | M03 | Task | Medium |  |  | Backlog
Create server SDK proof of concept | Send ASP.NET Core exception occurrences through a protected endpoint. | M03 – Error Tracking |  |  |  |  | Epic M03.1 – Error capture |  | M03 | Task | Medium |  |  | Backlog
Implement sensitive-data scrubbing | Redact tokens, credentials, form values and configured patterns. | M03 – Error Tracking |  |  |  |  | Epic M03.1 – Error capture |  | M03 | Task | Medium |  |  | Backlog
Add environment and release fields | Attach deployment identity to each occurrence. | M03 – Error Tracking |  |  |  |  | Epic M03.1 – Error capture |  | M03 | Task | Medium |  |  | Backlog
Epic M03.2 – Grouping and issue lifecycle | Turn many occurrences into manageable issues. | M03 – Error Tracking | [6 empty] | M03 | Epic | High | 1 week |  | Backlog
Design occurrence storage | Store high-volume occurrences separately from issue metadata. | M03 – Error Tracking |  |  |  |  | Epic M03.2 – Grouping and issue lifecycle |  | M03 | Task | Medium |  |  | Backlog
Implement error fingerprinting | Group by normalized type, stack and configured fingerprint. | M03 – Error Tracking |  |  |  |  | Epic M03.2 – Grouping and issue lifecycle |  | M03 | Task | Medium |  |  | Backlog
Implement issue states | Support unresolved, investigating, ignored and resolved. | M03 – Error Tracking |  |  |  |  | Epic M03.2 – Grouping and issue lifecycle |  | M03 | Task | Medium |  |  | Backlog
Detect regressions | Reopen or flag an issue that returns after resolution. | M03 – Error Tracking |  |  |  |  | Epic M03.2 – Grouping and issue lifecycle |  | M03 | Task | Medium |  |  | Backlog
Implement source-map upload | Associate uploaded maps with site and release. | M03 – Error Tracking |  |  |  |  | Epic M03.2 – Grouping and issue lifecycle |  | M03 | Task | Medium |  |  | Backlog
Resolve stack traces | Produce readable frames without exposing private source maps publicly. | M03 – Error Tracking |  |  |  |  | Epic M03.2 – Grouping and issue lifecycle |  | M03 | Task | Medium |  |  | Backlog
Epic M03.3 – Error dashboard | Show impact and trends. | M03 – Error Tracking | [6 empty] | M03 | Epic | High | 1 week |  | Backlog
Create issue inbox | Sort by newness, frequency, affected sessions and severity. | M03 – Error Tracking |  |  |  |  | Epic M03.3 – Error dashboard |  | M03 | Task | Medium |  |  | Backlog
Create issue detail page | Show stack, occurrences, releases, pages and browser segments. | M03 – Error Tracking |  |  |  |  | Epic M03.3 – Error dashboard |  | M03 | Task | Medium |  |  | Backlog
Create affected-user estimates | Use privacy-safe identifiers and explain the counting window. | M03 – Error Tracking |  |  |  |  | Epic M03.3 – Error dashboard |  | M03 | Task | Medium |  |  | Backlog
Create error trend charts | Compare occurrence rates over time. | M03 – Error Tracking |  |  |  |  | Epic M03.3 – Error dashboard |  | M03 | Task | Medium |  |  | Backlog
Publish issue change events | Enable alerting and AI without direct service coupling. | M03 – Error Tracking |  |  |  |  | Epic M03.3 – Error dashboard |  | M03 | Task | Medium |  |  | Backlog
M04 Milestone – Deployment Intelligence ready | The deployment intelligence module is independently deployable, observable and available in the shared dashboard. | M04 – Deployment Intelligence | [6 empty] | M04 | Milestone | High |  | M04 Complete | Backlog
Epic M04.1 – Deployment ingestion | Create a provider-neutral release and deployment model. | M04 – Deployment Intelligence | [6 empty] | M04 | Epic | High | 1 week |  | Backlog
Design release and deployment entities | Separate immutable release identity from environment deployment. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.1 – Deployment ingestion |  | M04 | Task | Medium |  |  | Backlog
Create generic deployment webhook | Validate signed provider-neutral events. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.1 – Deployment ingestion |  | M04 | Task | Medium |  |  | Backlog
Create GitHub Actions integration | Publish repository, commit, environment, result and timestamps. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.1 – Deployment ingestion |  | M04 | Task | Medium |  |  | Backlog
Create deployment status workflow | Support started, succeeded, failed and rolled-back states. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.1 – Deployment ingestion |  | M04 | Task | Medium |  |  | Backlog
Publish deployment events | Notify other modules through versioned contracts. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.1 – Deployment ingestion |  | M04 | Task | Medium |  |  | Backlog
Epic M04.2 – Release correlation | Relate data-module events to releases. | M04 – Deployment Intelligence | [6 empty] | M04 | Epic | High | 1 week |  | Backlog
Add release field to browser SDK configuration | Expose the deployed version without coupling to GitHub. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.2 – Release correlation |  | M04 | Task | Medium |  |  | Backlog
Subscribe analytics to release metadata | Allow release filtering through service APIs. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.2 – Release correlation |  | M04 | Task | Medium |  |  | Backlog
Subscribe performance to release metadata | Enable regressions by release. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.2 – Release correlation |  | M04 | Task | Medium |  |  | Backlog
Subscribe error tracking to release metadata | Identify new and regressed issues. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.2 – Release correlation |  | M04 | Task | Medium |  |  | Backlog
Create before-and-after comparison API | Use consistent windows and minimum sample checks. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.2 – Release correlation |  | M04 | Task | Medium |  |  | Backlog
Epic M04.3 – Deployment dashboard | Provide a clear release history. | M04 – Deployment Intelligence | [6 empty] | M04 | Epic | High | 1 week |  | Backlog
Create deployment timeline | Show environment, commit, actor, status and links. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.3 – Deployment dashboard |  | M04 | Task | Medium |  |  | Backlog
Create release health summary | Compose analytics, performance and errors through APIs. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.3 – Deployment dashboard |  | M04 | Task | Medium |  |  | Backlog
Create suspected regression badge | Use explicit rules rather than AI-only judgement. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.3 – Deployment dashboard |  | M04 | Task | Medium |  |  | Backlog
Create rollback annotation | Show rollback and recovery effects. | M04 – Deployment Intelligence |  |  |  |  | Epic M04.3 – Deployment dashboard |  | M04 | Task | Medium |  |  | Backlog
M05 Milestone – Goals and Funnels ready | The goals and funnels module is independently deployable, observable and available in the shared dashboard. | M05 – Goals and Funnels | [6 empty] | M05 | Milestone | High |  | M05 Complete | Backlog
Epic M05.1 – Goal configuration | Define conversions independently from website code. | M05 – Goals and Funnels | [6 empty] | M05 | Epic | High | 1 week |  | Backlog
Create goal entity and versioning | Preserve historical meaning after a goal changes. | M05 – Goals and Funnels |  |  |  |  | Epic M05.1 – Goal configuration |  | M05 | Task | Medium |  |  | Backlog
Support page-based goals | Match normalized page rules. | M05 – Goals and Funnels |  |  |  |  | Epic M05.1 – Goal configuration |  | M05 | Task | Medium |  |  | Backlog
Support custom-event goals | Match named events and allowlisted properties. | M05 – Goals and Funnels |  |  |  |  | Epic M05.1 – Goal configuration |  | M05 | Task | Medium |  |  | Backlog
Add goal management UI | Create, test, enable and archive goals. | M05 – Goals and Funnels |  |  |  |  | Epic M05.1 – Goal configuration |  | M05 | Task | Medium |  |  | Backlog
Publish goal configuration events | Update processors without shared database access. | M05 – Goals and Funnels |  |  |  |  | Epic M05.1 – Goal configuration |  | M05 | Task | Medium |  |  | Backlog
Epic M05.2 – Funnel engine | Calculate ordered journeys. | M05 – Goals and Funnels | [6 empty] | M05 | Epic | High | 1 week |  | Backlog
Create funnel definition model | Define steps, ordering, window and optionality. | M05 – Goals and Funnels |  |  |  |  | Epic M05.2 – Funnel engine |  | M05 | Task | Medium |  |  | Backlog
Implement funnel processor | Calculate entry, completion and drop-off from analytics events. | M05 – Goals and Funnels |  |  |  |  | Epic M05.2 – Funnel engine |  | M05 | Task | Medium |  |  | Backlog
Implement attribution window | Document how conversions are associated with acquisition data. | M05 – Goals and Funnels |  |  |  |  | Epic M05.2 – Funnel engine |  | M05 | Task | Medium |  |  | Backlog
Add segment support | Filter funnels by source, device, country and page. | M05 – Goals and Funnels |  |  |  |  | Epic M05.2 – Funnel engine |  | M05 | Task | Medium |  |  | Backlog
Create reconciliation tests | Use deterministic event journeys and expected outcomes. | M05 – Goals and Funnels |  |  |  |  | Epic M05.2 – Funnel engine |  | M05 | Task | Medium |  |  | Backlog
Epic M05.3 – Conversion dashboard | Make conversion analysis useful. | M05 – Goals and Funnels | [6 empty] | M05 | Epic | High | 1 week |  | Backlog
Create goal overview | Show conversions, rate and trend. | M05 – Goals and Funnels |  |  |  |  | Epic M05.3 – Conversion dashboard |  | M05 | Task | Medium |  |  | Backlog
Create funnel visualization | Show counts and drop-off per step. | M05 – Goals and Funnels |  |  |  |  | Epic M05.3 – Conversion dashboard |  | M05 | Task | Medium |  |  | Backlog
Create acquisition conversion view | Compare channels and campaigns. | M05 – Goals and Funnels |  |  |  |  | Epic M05.3 – Conversion dashboard |  | M05 | Task | Medium |  |  | Backlog
Create device conversion view | Identify device-specific friction. | M05 – Goals and Funnels |  |  |  |  | Epic M05.3 – Conversion dashboard |  | M05 | Task | Medium |  |  | Backlog
Add CSV export | Export aggregated, permission-checked results. | M05 – Goals and Funnels |  |  |  |  | Epic M05.3 – Conversion dashboard |  | M05 | Task | Medium |  |  | Backlog
M06 Milestone – SEO and Content Quality ready | The seo and content quality module is independently deployable, observable and available in the shared dashboard. | M06 – SEO and Content Quality | [6 empty] | M06 | Milestone | High |  | M06 Complete | Backlog
Epic M06.1 – Safe crawler | Crawl registered sites with explicit limits. | M06 – SEO and Content Quality | [6 empty] | M06 | Epic | High | 1 week |  | Backlog
Create crawl scheduler | Queue recurring and manual scans. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.1 – Safe crawler |  | M06 | Task | Medium |  |  | Backlog
Implement robots and sitemap discovery | Respect configured crawl boundaries. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.1 – Safe crawler |  | M06 | Task | Medium |  |  | Backlog
Implement URL normalization and deduplication | Avoid loops and repeated content. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.1 – Safe crawler |  | M06 | Task | Medium |  |  | Backlog
Implement rate and depth limits | Protect both the target site and the scanner. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.1 – Safe crawler |  | M06 | Task | Medium |  |  | Backlog
Store crawl evidence | Keep status, headers and selected metadata without full private page content. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.1 – Safe crawler |  | M06 | Task | Medium |  |  | Backlog
Epic M06.2 – SEO checks | Generate actionable technical findings. | M06 – SEO and Content Quality | [6 empty] | M06 | Epic | High | 1 week |  | Backlog
Check titles and descriptions | Detect missing, duplicate or unreasonable metadata. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.2 – SEO checks |  | M06 | Task | Medium |  |  | Backlog
Check canonical and index directives | Report conflicting or missing signals. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.2 – SEO checks |  | M06 | Task | Medium |  |  | Backlog
Check heading structure | Report evidence without pretending automated checks prove quality. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.2 – SEO checks |  | M06 | Task | Medium |  |  | Backlog
Check broken internal links | Record source and target URLs. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.2 – SEO checks |  | M06 | Task | Medium |  |  | Backlog
Check sitemap and robots consistency | Identify unreachable or blocked important URLs. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.2 – SEO checks |  | M06 | Task | Medium |  |  | Backlog
Run Lighthouse CLI job | Store report summaries and selected raw artifacts. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.2 – SEO checks |  | M06 | Task | Medium |  |  | Backlog
Epic M06.3 – SEO dashboard | Show issues and progress over time. | M06 – SEO and Content Quality | [6 empty] | M06 | Epic | High | 1 week |  | Backlog
Create SEO overview | Show issue counts, affected pages and scan history. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.3 – SEO dashboard |  | M06 | Task | Medium |  |  | Backlog
Create issue detail view | Show evidence, severity and remediation guidance. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.3 – SEO dashboard |  | M06 | Task | Medium |  |  | Backlog
Create page inventory | Filter by status, indexability and issue count. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.3 – SEO dashboard |  | M06 | Task | Medium |  |  | Backlog
Create historical comparison | Compare issue changes between scans. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.3 – SEO dashboard |  | M06 | Task | Medium |  |  | Backlog
Publish scan result events | Enable alerting and AI subscriptions. | M06 – SEO and Content Quality |  |  |  |  | Epic M06.3 – SEO dashboard |  | M06 | Task | Medium |  |  | Backlog
M07 Milestone – Heatmaps and Session Insights ready | The heatmaps and session insights module is independently deployable, observable and available in the shared dashboard. | M07 – Heatmaps and Session Insights | [6 empty] | M07 | Milestone | High |  | M07 Complete | Backlog
Epic M07.1 – Interaction collection | Collect minimal interaction data with strong privacy defaults. | M07 – Heatmaps and Session Insights | [6 empty] | M07 | Epic | High | 1 week |  | Backlog
Define blocked elements and attributes | Never collect input values, passwords or sensitive marked content. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.1 – Interaction collection |  | M07 | Task | Medium |  |  | Backlog
Collect normalized click positions | Store element-independent coordinates and viewport context. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.1 – Interaction collection |  | M07 | Task | Medium |  |  | Backlog
Collect scroll-depth summaries | Send bounded percentage milestones rather than continuous raw motion. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.1 – Interaction collection |  | M07 | Task | Medium |  |  | Backlog
Implement sampling and caps | Limit sessions and events per session. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.1 – Interaction collection |  | M07 | Task | Medium |  |  | Backlog
Create privacy test pages | Verify masking and blocked-data behavior. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.1 – Interaction collection |  | M07 | Task | Medium |  |  | Backlog
Epic M07.2 – Heatmap processing | Aggregate interactions across responsive layouts. | M07 – Heatmaps and Session Insights | [6 empty] | M07 | Epic | High | 1 week |  | Backlog
Create interaction storage schema | Partition by site, page, viewport class and date. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.2 – Heatmap processing |  | M07 | Task | Medium |  |  | Backlog
Normalize responsive viewport groups | Avoid combining incompatible layouts. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.2 – Heatmap processing |  | M07 | Task | Medium |  |  | Backlog
Aggregate click density | Produce queryable bins or points. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.2 – Heatmap processing |  | M07 | Task | Medium |  |  | Backlog
Aggregate scroll reach | Calculate reach by page depth. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.2 – Heatmap processing |  | M07 | Task | Medium |  |  | Backlog
Implement retention cleanup | Use shorter defaults than ordinary page analytics. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.2 – Heatmap processing |  | M07 | Task | Medium |  |  | Backlog
Epic M07.3 – Heatmap dashboard | Render useful interaction views. | M07 – Heatmaps and Session Insights | [6 empty] | M07 | Epic | High | 1 week |  | Backlog
Create screenshot/version strategy | Avoid overlaying events on a changed page without warning. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.3 – Heatmap dashboard |  | M07 | Task | Medium |  |  | Backlog
Create click heatmap renderer | Support viewport and date filters. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.3 – Heatmap dashboard |  | M07 | Task | Medium |  |  | Backlog
Create scroll heatmap renderer | Show percentage of sessions reaching page regions. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.3 – Heatmap dashboard |  | M07 | Task | Medium |  |  | Backlog
Create element click table | Show safe selector summaries where available. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.3 – Heatmap dashboard |  | M07 | Task | Medium |  |  | Backlog
Add privacy and sample warnings | Display masking, sample count and page-version limitations. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.3 – Heatmap dashboard |  | M07 | Task | Medium |  |  | Backlog
Epic M07.4 – Optional session replay proof of concept | Treat replay as a separate high-risk slice. | M07 – Heatmaps and Session Insights | [6 empty] | M07 | Epic | High | 1 week |  | Backlog
Write replay privacy design | Define exact captured mutations and masking behavior. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.4 – Optional session replay proof of concept |  | M07 | Task | Medium |  |  | Backlog
Store encrypted replay chunks | Use object storage with short retention. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.4 – Optional session replay proof of concept |  | M07 | Task | Medium |  |  | Backlog
Create controlled replay player | Restrict access and log every viewing action. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.4 – Optional session replay proof of concept |  | M07 | Task | Medium |  |  | Backlog
Run privacy review before release | Do not enable replay by default. | M07 – Heatmaps and Session Insights |  |  |  |  | Epic M07.4 – Optional session replay proof of concept |  | M07 | Task | Medium |  |  | Backlog
M08 Milestone – AI Insights ready | The ai insights module is independently deployable, observable and available in the shared dashboard. | M08 – AI Insights | [6 empty] | M08 | Milestone | High |  | M08 Complete | Backlog
Epic M08.1 – AI safety and architecture | Keep Claude behind explicit, auditable application tools. | M08 – AI Insights | [6 empty] | M08 | Epic | High | 1 week |  | Backlog
Create AI provider interface | Support Claude and a deterministic fake provider. | M08 – AI Insights |  |  |  |  | Epic M08.1 – AI safety and architecture |  | M08 | Task | Medium |  |  | Backlog
Define typed metric tools | Expose only approved query shapes and limits. | M08 – AI Insights |  |  |  |  | Epic M08.1 – AI safety and architecture |  | M08 | Task | Medium |  |  | Backlog
Implement workspace authorization per tool | Check every tool call independently. | M08 – AI Insights |  |  |  |  | Epic M08.1 – AI safety and architecture |  | M08 | Task | Medium |  |  | Backlog
Implement prompt and tool versioning | Make generated output reproducible enough to audit. | M08 – AI Insights |  |  |  |  | Epic M08.1 – AI safety and architecture |  | M08 | Task | Medium |  |  | Backlog
Implement usage budgets | Limit requests and tokens by workspace and module. | M08 – AI Insights |  |  |  |  | Epic M08.1 – AI safety and architecture |  | M08 | Task | Medium |  |  | Backlog
Implement AI audit records | Store request purpose, tools, metrics, result and reviewer feedback. | M08 – AI Insights |  |  |  |  | Epic M08.1 – AI safety and architecture |  | M08 | Task | Medium |  |  | Backlog
Epic M08.2 – Insight generation | Generate evidence-based explanations. | M08 – AI Insights | [6 empty] | M08 | Epic | High | 1 week |  | Backlog
Create weekly site summary | Compare explicit periods and highlight material changes. | M08 – AI Insights |  |  |  |  | Epic M08.2 – Insight generation |  | M08 | Task | Medium |  |  | Backlog
Create traffic-change analysis | Use acquisition, page and device tools. | M08 – AI Insights |  |  |  |  | Epic M08.2 – Insight generation |  | M08 | Task | Medium |  |  | Backlog
Create performance-regression analysis | Use percentile and release data when available. | M08 – AI Insights |  |  |  |  | Epic M08.2 – Insight generation |  | M08 | Task | Medium |  |  | Backlog
Create error-spike analysis | Use issue and release data when available. | M08 – AI Insights |  |  |  |  | Epic M08.2 – Insight generation |  | M08 | Task | Medium |  |  | Backlog
Create SEO scan summary | Summarize evidence from completed scans. | M08 – AI Insights |  |  |  |  | Epic M08.2 – Insight generation |  | M08 | Task | Medium |  |  | Backlog
Create unsupported-claim guard | Require metric evidence and express uncertainty. | M08 – AI Insights |  |  |  |  | Epic M08.2 – Insight generation |  | M08 | Task | Medium |  |  | Backlog
Epic M08.3 – AI dashboard experience | Make insights reviewable rather than magical. | M08 – AI Insights | [6 empty] | M08 | Epic | High | 1 week |  | Backlog
Create AI insights feed | Show period, sources, confidence and generation time. | M08 – AI Insights |  |  |  |  | Epic M08.3 – AI dashboard experience |  | M08 | Task | Medium |  |  | Backlog
Create ask-data workflow | Offer constrained questions and follow-ups. | M08 – AI Insights |  |  |  |  | Epic M08.3 – AI dashboard experience |  | M08 | Task | Medium |  |  | Backlog
Show tool evidence | List the metrics and filters used for each conclusion. | M08 – AI Insights |  |  |  |  | Epic M08.3 – AI dashboard experience |  | M08 | Task | Medium |  |  | Backlog
Add feedback and correction | Let the user mark useful, wrong or missing context. | M08 – AI Insights |  |  |  |  | Epic M08.3 – AI dashboard experience |  | M08 | Task | Medium |  |  | Backlog
Create scheduled insight job | Generate only when enough new data exists. | M08 – AI Insights |  |  |  |  | Epic M08.3 – AI dashboard experience |  | M08 | Task | Medium |  |  | Backlog
M09 Milestone – Alerts and Uptime ready | The alerts and uptime module is independently deployable, observable and available in the shared dashboard. | M09 – Alerts and Uptime | [6 empty] | M09 | Milestone | High |  | M09 Complete | Backlog
Epic M09.1 – Uptime monitoring | Run independent availability checks. | M09 – Alerts and Uptime | [6 empty] | M09 | Epic | High | 1 week |  | Backlog
Create monitor configuration | Support HTTP URL, interval, timeout and expected status. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.1 – Uptime monitoring |  | M09 | Task | Medium |  |  | Backlog
Create scheduled check worker | Run checks independently per monitor. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.1 – Uptime monitoring |  | M09 | Task | Medium |  |  | Backlog
Store check results | Keep latency, status and failure reason. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.1 – Uptime monitoring |  | M09 | Task | Medium |  |  | Backlog
Implement consecutive-failure rule | Avoid alerting on one transient failure. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.1 – Uptime monitoring |  | M09 | Task | Medium |  |  | Backlog
Create uptime dashboard | Show current status, history and availability. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.1 – Uptime monitoring |  | M09 | Task | Medium |  |  | Backlog
Epic M09.2 – Cross-module alert engine | Evaluate metrics without querying module databases. | M09 – Alerts and Uptime | [6 empty] | M09 | Epic | High | 1 week |  | Backlog
Create alert-rule model | Support threshold, comparison, duration and cooldown. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.2 – Cross-module alert engine |  | M09 | Task | Medium |  |  | Backlog
Create metric provider contracts | Read approved metrics from module APIs or published summaries. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.2 – Cross-module alert engine |  | M09 | Task | Medium |  |  | Backlog
Implement evaluation worker | Evaluate enabled rules on schedule or event. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.2 – Cross-module alert engine |  | M09 | Task | Medium |  |  | Backlog
Implement deduplication and recovery | Create open, repeated and recovered alert states. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.2 – Cross-module alert engine |  | M09 | Task | Medium |  |  | Backlog
Create silence and maintenance windows | Prevent expected deployment noise. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.2 – Cross-module alert engine |  | M09 | Task | Medium |  |  | Backlog
Epic M09.3 – Notification delivery | Deliver alerts reliably. | M09 – Alerts and Uptime | [6 empty] | M09 | Epic | High | 1 week |  | Backlog
Create email channel | Send templated notifications and record outcomes. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.3 – Notification delivery |  | M09 | Task | Medium |  |  | Backlog
Create Microsoft Teams channel | Send adaptive-card or webhook notifications. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.3 – Notification delivery |  | M09 | Task | Medium |  |  | Backlog
Create generic webhook channel | Sign outgoing payloads. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.3 – Notification delivery |  | M09 | Task | Medium |  |  | Backlog
Implement retry and dead-letter handling | Recover transient delivery failures. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.3 – Notification delivery |  | M09 | Task | Medium |  |  | Backlog
Create alert history and acknowledgement UI | Show status, evidence and delivery attempts. | M09 – Alerts and Uptime |  |  |  |  | Epic M09.3 – Notification delivery |  | M09 | Task | Medium |  |  | Backlog
M10 Milestone – Multi-site and Team Hardening ready | The multi-site and team hardening module is independently deployable, observable and available in the shared dashboard. | M10 – Multi-site and Team Hardening | [6 empty] | M10 | Milestone | High |  | M10 Complete | Backlog
Epic M10.1 – Workspace security | Strengthen tenant isolation and access. | M10 – Multi-site and Team Hardening | [6 empty] | M10 | Epic | High | 1 week |  | Backlog
Create invitation workflow | Invite and remove members safely. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.1 – Workspace security |  | M10 | Task | Medium |  |  | Backlog
Add module-level permissions | Restrict sensitive modules such as replay and errors. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.1 – Workspace security |  | M10 | Task | Medium |  |  | Backlog
Add authorization integration tests | Prove cross-workspace access is rejected. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.1 – Workspace security |  | M10 | Task | Medium |  |  | Backlog
Add audit-log viewer | Show security and configuration changes. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.1 – Workspace security |  | M10 | Task | Medium |  |  | Backlog
Add API key scopes | Separate event publishing, administration and integrations. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.1 – Workspace security |  | M10 | Task | Medium |  |  | Backlog
Epic M10.2 – Usage and lifecycle | Control cost and data lifecycle. | M10 – Multi-site and Team Hardening | [6 empty] | M10 | Epic | High | 1 week |  | Backlog
Implement event quotas | Enforce per-site daily or monthly volume. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.2 – Usage and lifecycle |  | M10 | Task | Medium |  |  | Backlog
Implement adaptive sampling | Reduce optional event types when approaching limits. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.2 – Usage and lifecycle |  | M10 | Task | Medium |  |  | Backlog
Create usage dashboard | Show accepted, sampled and rejected volume. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.2 – Usage and lifecycle |  | M10 | Task | Medium |  |  | Backlog
Create site data export | Export permission-checked data in documented formats. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.2 – Usage and lifecycle |  | M10 | Task | Medium |  |  | Backlog
Create site deletion workflow | Delete service-owned data through events and completion tracking. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.2 – Usage and lifecycle |  | M10 | Task | Medium |  |  | Backlog
Epic M10.3 – Operations | Make self-hosting and upgrades safe. | M10 – Multi-site and Team Hardening | [6 empty] | M10 | Epic | High | 1 week |  | Backlog
Create versioned deployment manifests | Pin service and infrastructure versions. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.3 – Operations |  | M10 | Task | Medium |  |  | Backlog
Create backup schedule and verification | Test restore, not just backup creation. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.3 – Operations |  | M10 | Task | Medium |  |  | Backlog
Create upgrade runbook | Document order, migrations and rollback. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.3 – Operations |  | M10 | Task | Medium |  |  | Backlog
Create resource monitoring | Show CPU, memory, storage and queue depth. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.3 – Operations |  | M10 | Task | Medium |  |  | Backlog
Create disaster recovery exercise | Recover a development copy from backups. | M10 – Multi-site and Team Hardening |  |  |  |  | Epic M10.3 – Operations |  | M10 | Task | Medium |  |  | Backlog
M11 Milestone – C++ Edge Agent ready | The c++ edge agent module is independently deployable, observable and available in the shared dashboard. | M11 – C++ Edge Agent | [6 empty] | M11 | Milestone | High |  | M11 Complete | Backlog
Epic M11.1 – Agent core | Build a small and portable native agent. | M11 – C++ Edge Agent | [6 empty] | M11 | Epic | High | 1 week |  | Backlog
Create CMake project and CI matrix | Build supported operating-system targets. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.1 – Agent core |  | M11 | Task | Medium |  |  | Backlog
Implement configuration model | Read endpoint, enrollment, probes and intervals securely. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.1 – Agent core |  | M11 | Task | Medium |  |  | Backlog
Implement HTTP client | Send authenticated batched observations. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.1 – Agent core |  | M11 | Task | Medium |  |  | Backlog
Implement encrypted local queue | Buffer measurements during network loss. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.1 – Agent core |  | M11 | Task | Medium |  |  | Backlog
Implement graceful shutdown | Flush bounded data and close cleanly. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.1 – Agent core |  | M11 | Task | Medium |  |  | Backlog
Epic M11.2 – System and network probes | Collect useful host observations. | M11 – C++ Edge Agent | [6 empty] | M11 | Epic | High | 1 week |  | Backlog
Collect CPU and memory metrics | Use platform abstractions and normalized units. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.2 – System and network probes |  | M11 | Task | Medium |  |  | Backlog
Collect disk usage | Track configured mounts only. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.2 – System and network probes |  | M11 | Task | Medium |  |  | Backlog
Implement HTTP probe | Measure status, DNS, connection and total latency. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.2 – System and network probes |  | M11 | Task | Medium |  |  | Backlog
Implement TCP probe | Test endpoint reachability without application-specific logic. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.2 – System and network probes |  | M11 | Task | Medium |  |  | Backlog
Implement backoff and jitter | Avoid synchronized retry storms. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.2 – System and network probes |  | M11 | Task | Medium |  |  | Backlog
Epic M11.3 – Enrollment and dashboard | Operate agents safely. | M11 – C++ Edge Agent | [6 empty] | M11 | Epic | High | 1 week |  | Backlog
Create one-time enrollment token | Exchange a short-lived token for an agent credential. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.3 – Enrollment and dashboard |  | M11 | Task | Medium |  |  | Backlog
Create agent registry API | Track version, last seen, site and assigned checks. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.3 – Enrollment and dashboard |  | M11 | Task | Medium |  |  | Backlog
Create agent status dashboard | Show online state, version and buffered failures. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.3 – Enrollment and dashboard |  | M11 | Task | Medium |  |  | Backlog
Create remote configuration pull | Fetch signed, scoped configuration. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.3 – Enrollment and dashboard |  | M11 | Task | Medium |  |  | Backlog
Create package and install documentation | Provide an understandable demo installation. | M11 – C++ Edge Agent |  |  |  |  | Epic M11.3 – Enrollment and dashboard |  | M11 | Task | Medium |  |  | Backlog

## Service Catalog
Service | Technology | Responsibility | Owned Data | Integration | Introduced
Web Dashboard | Vue 3 / TypeScript | User interface and visualizations | No primary business data | HTTPS through Gateway | All modules
API Gateway / BFF | ASP.NET Core | Single authenticated API surface and response composition | No module-owned data | HTTP/gRPC to internal services | M00
Identity & Workspace Service | ASP.NET Core | Users, workspaces, roles and invitations | PostgreSQL identity database | workspace.created, membership.changed | M00/M10
Site Registry Service | ASP.NET Core | Sites, domains, settings, SDK keys and module enablement | PostgreSQL site database | site.created, site.settings.changed | M00
Event Collector | ASP.NET Core | Validate and accept browser/agent events quickly | Short-lived buffers only | Publishes versioned CloudEvents | M01+
Analytics Processor | C# Worker | Normalize, deduplicate and enrich analytics events | ClickHouse analytics tables | Consumes analytics.received; publishes analytics.processed | M01
Analytics Query Service | ASP.NET Core | Metric definitions and read-optimized analytics queries | Owns ClickHouse analytics schema | HTTP/gRPC; no direct cross-service DB access | M01
Performance Service | ASP.NET Core + Worker | Process and query real-user performance data | ClickHouse performance schema | Consumes performance.received | M02
Error Service | ASP.NET Core + Worker | Group occurrences and manage error issues | PostgreSQL metadata + ClickHouse occurrences | Consumes error.received; publishes error.issue.changed | M03
Deployment Service | ASP.NET Core | Releases, deployments and provider webhooks | PostgreSQL deployment database | deployment.completed, release.created | M04
Conversion Service | ASP.NET Core + Worker | Goals, funnels and attribution | PostgreSQL config + ClickHouse rollups | Consumes analytics.processed | M05
SEO Scanner | C# Worker / Container Job | Scheduled crawl and Lighthouse execution | PostgreSQL scan metadata + object storage reports | seo.scan.completed | M06
Session Insights Service | ASP.NET Core + Worker | Heatmap samples and optional replay chunks | ClickHouse + object storage | Consumes interaction.received | M07
AI Insights Service | ASP.NET Core | Controlled AI tools, reports and audit | PostgreSQL AI audit database | Calls read APIs; publishes insight.generated | M08
Alerting Service | ASP.NET Core + Worker | Rules, evaluations and notification orchestration | PostgreSQL alert database | Subscribes to module metric events | M09
Notification Service | C# Worker | Email, Teams and webhook delivery | PostgreSQL delivery log | Consumes notification.requested | M09
C++ Edge Agent | C++ | Host and endpoint telemetry | Local encrypted buffer | HTTPS to Event Collector | M11

## Event Contracts
Event Type | Publisher | Subscribers | Purpose
site.created.v1 | Site Registry | All interested modules | A site was registered and is available for module initialization.
site.settings.changed.v1 | Site Registry | Collectors and module services | Tracking, sampling, retention or privacy configuration changed.
analytics.page-view.received.v1 | Event Collector | Analytics Processor | A validated page-view event was accepted.
analytics.custom-event.received.v1 | Event Collector | Analytics Processor / Conversion Service | A validated custom event was accepted.
analytics.processed.v1 | Analytics Processor | Conversion / Alerting / AI | An analytics event was normalized and included in metrics.
performance.sample.received.v1 | Event Collector | Performance Service | A browser performance sample was accepted.
error.occurrence.received.v1 | Event Collector | Error Service | A browser or API error occurrence was accepted.
error.issue.changed.v1 | Error Service | Alerting / AI | An issue was created, regressed, resolved or changed severity.
deployment.completed.v1 | Deployment Service | Analytics / Performance / Error / AI | A deployment completed for a site and environment.
seo.scan.completed.v1 | SEO Scanner | Alerting / AI | A scheduled SEO scan finished.
insight.generated.v1 | AI Insights | Dashboard / Notification | A reviewed or generated insight is available.
notification.requested.v1 | Any module | Notification Service | A delivery request was created through a supported channel.

## Board Setup
Telumera Asana Board Setup
Recommended project | Telumera Platform
Section strategy | Use one section per module (M00–M11). Track workflow with the Status custom field.
Import order | Import the supplied CSV into a new or empty Asana project. Parent Epic rows appear before their subtasks.
Name | Purpose / suggested values
Module | M00–M11
Work Type | Milestone, Epic, Task, Bug, Spike, ADR
Status | Backlog, Ready, In Progress, Review, Blocked, Done
Priority | Critical, High, Medium, Low
Estimate | Hours or development days
Milestone | Module completion marker
Risk | Low, Medium, High
Architecture Area | UI, API, Worker, Data, Messaging, Infrastructure, Security, AI
Suggested board view | Group by Status; filter to the current Module.
Suggested list view | Group by Section/Module and sort Work Type: Milestone, Epic, Task.
Suggested first milestone | M00 Platform foundation ready
Suggested first product release | M01 Portfolio analytics live